## Summary
Week: | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Date: | 2025-09-21 | 2025-09-28 | 2025-10-05 | 2025-10-12 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-23
Research | Proposal Changes |  |  | Milestone #1 |  |  | Milestone #2 |  |  | Final Presentation
Project Setup
Research
Writing |  | Research Implementation
ERD
Application Story Board
System Diagrams
Implementation |  |  |  | Standup Dev. Env.
Database Standup
Build Development Environment
Production Standup
Production Migration
Documentation/Final Deliverables
Testing | [5 empty] | Testing & Feedback
Row Labels | Sum of Time (Mins)
Other (See Notes) | 270
Research | 600
(blank)
Research Implementation | 360
Application Story Board | 75
Grand Total | 1305

## Time_Log
Date | Time (Mins) | Task | Notes
2025-09-27 | 60 | Other (See Notes) | Creating initial documentations and workflow setup
2025-09-27 | 120 | Other (See Notes) | Creating workbook, standup log template, and workflow documentation
2025-09-28 | 60 | Research | CMMC background
2025-09-28 | 120 | Research | CMMC resources
2025-09-29 | 105 | Research | CMMC resources
2025-10-04 | 45 | Research | Culmniating resources
2025-10-04 | 120 | Research | CMMC Challenges
2025-10-04 | 105 | Research Implementation | Wrote main webpage statements
2025-10-05 | 150 | Research | CMMC Research wrap-up
2025-10-06 | 90 | Research Implementation | Started dictionary, and assement writeups
2025-10-10 | 75 | Research Implementation
2025-10-11 | 90 | Research Implementation
2025-10-12 | 75 | Application Story Board | Worked on storyboards
2025-10-14 | 90 | Other (See Notes) | Fixing documentation, MISC.
2025-10-14 | 135 | Application Story Board | Built out first two slides and brainstormed ideas for following slides
2025-10-14 | 45 | Final Deliverables | Building Milestone 1 Presentation
2025-10-14 | 60 | ERD | ERD built
2025-10-14 | 30 | System Diagrams | Local Host System Diagram
2025-10-15 | 30 | Other (See Notes) | Pushing everything to Git
2025-10-15 | 30 | System Diagrams | Fixed lost ERD
2025-10-15 | 15 | Other (See Notes) | Edited Git README
2025-10-16 | 75 | Final Deliverables | Milestone #1 report
2025-10-16 | 15 | Other (See Notes) | Fixed naming conventions of files, added warning to README due to the likelihood of the the repo going public
2025-10-16 | 60 | Other (See Notes) | Standup log and MISC documentation
2025-10-16 | 75 | Application Story Board | Finsihing up starter storboards
2025-10-16 | 45 | Final Deliverables | Building Milestone 1 Presentation
2025-10-16 | 60 | Final Deliverables | Finalized presentation and Milestone 1 report
2025-10-20 | 90 | Standup Dev. Env. | Dev Env. Stood up
2025-10-20 | 105 | Database Standup | Database outline created and implemented
2025-10-20 | 90 | Database Standup | Added CUI types
2025-10-21 | 60 | Build Dev. Env. | File decisions made
2025-10-21 | 90 | Build Dev. Env. | Fixed issues with XAMPP
2025-10-25 | 180 | Build Dev. Env. | worked on basic layout
2025-10-26 | 90 | Build Dev. Env. | worked on basic layout

## BACKGROUND_LOGIC
Tasks | Time Spent | Estimated Time left
Proposal Changes | 2685 | 6015
Research
Research Implementation
ERD
Application Story Board
System Diagrams
Standup Dev. Env.
Database Standup
Build Dev. Env.
Production Standup
Production Migration
Final Deliverables
Testing
Other (See Notes)